## Slide 1: Chapter 12: Project Procurement Management
Note: See the text itself for full citations.
Information Technology Project Management, Sixth Edition

## Slide 2: Announcements
10/27 - Chapter 7, then team breakouts
11/3 - Chapter 8, then team breakouts
11/10 - Chapter 9, then team breakouts
11/17 - Chapter 10 & 11
11/24 - No Class Happy Thanksgiving
12/1 - Chapter 12
12/8 - Final Demo presented; Final reports due
12/15 - Final Exam

## Slide 3: Learning Objectives
Understand the importance of project procurement management
Describe the work involved in planning procurements for projects, including determining the proper type of contract, preparing a procurement management plan, statement of work, source selection criteria, and make-or-buy analysis
Discuss what is involved in conducting procurements and strategies for obtaining seller responses, selecting sellers, and awarding contracts

## Slide 4: Learning Objectives (continued)
Understand the process of administering procurements by managing procurement relationships and monitoring contract performance
Describe the process of closing procurements

## Slide 5: REVIEW: Project Management Framework – 9 Knowledge Areas

## Slide 6: REVIEW:(continued)

## Slide 7: Figure 12-1. Project Procurement Management Summary

## Slide 8: Project Procurement Management Processes
Project procurement management: acquiring goods and services for a project from outside the performing organization
Processes include:
  Planning procurements: determining what to procure, when, and how
  Conducting procurements: obtaining seller responses, selecting sellers, and awarding contracts
  Administering procurements: managing relationships with sellers, monitoring contract performance, and making changes as needed
  Closing procurements: completing and settling each contract, including resolving of any open items

## Slide 9: Importance of Project Procurement Management
Procurement means acquiring goods and/or services from an outside source
Other terms include purchasing and outsourcing

## Slide 10: Planning Procurements
Identifying which project needs can best be met by using products or services outside the organization
If there is no need to buy any products or services from outside the organization, then there is no need to perform any of the other procurement management processes

## Slide 11: Tools and Techniques for Planning Purchases and Acquisitions
Build-or-buy analysis: general management technique used to determine whether an organization should make or perform a particular product or service inside the organization or buy from someone else
Often involves financial analysis
Experts, both internal and external, can provide valuable inputs in procurement decisions

## Slide 12: Build-or-Buy Example
Build the website yourself
  Pro’s: take your time, change things around, no cost for changes, you own code.
  Con’s: are it could take longer, maybe you don’t have the skillset, you will have to maintain
Have someone build it for you
  Pro’s– quicker, they have skillset.
  Con’s: have to be clear in what they are building, changes cost money, they might own the code, changes/maintenance might cost more in the long run.

## Slide 13: Key Terms : Contracts
A contract is a mutually binding agreement that obligates the seller to provide the specified products or services and obligates the buyer to pay for them
Contracts can clarify responsibilities and sharpen focus on key deliverables of a project
Because contracts are legally binding, there is more accountability for delivering the work as stated in the contract
A recent trend in outsourcing is the increasing size of contracts

## Slide 14: Types of Contracts
Different types of contracts can be used in different situations:
  Fixed price or lump sum contracts: involve a fixed total price for a well-defined product or service
  Cost reimbursable contracts: involve payment to the seller for direct and indirect costs
  Time and material contracts: hybrid of both fixed price and cost reimbursable contracts, often used by consultants
  Unit price contracts: require the buyer to pay the seller a predetermined amount per unit of service
A single contract can actually include all four of these categories if it makes sense for that particular procurement

## Slide 15: Contract Clauses
Contracts should include specific clauses that take into account issues that are unique to the project
Can require various educational or work experience for different pay rights
A termination clause is a contract clause that allows the buyer or supplier to end the contract

## Slide 16: Procurement Management Plan
Describes how the procurement processes will be managed, from developing documentation for making outside purchases or acquisitions to contract closure
Contents vary based on project needs

## Slide 17: Contract Statement of Work (SOW)
A statement of work is a description of the work required for the procurement
If a SOW is used as part of a contract to describe only the work required for that particular contract, it is called a contract statement of work
A SOW is a type of scope statement
A good SOW gives bidders a better understanding of the buyer’s expectations

## Slide 18: Figure 12-3. Statement of Work (SOW) Template

## Slide 19: Procurement Documents
Request for Proposals: used to solicit proposals from prospective sellers
  A proposal is a document prepared by a seller when there are different approaches for meeting buyer needs
Requests for Quotes: used to solicit quotes or bids from prospective suppliers
  A bid, also called a tender or quote (short for quotation), is a document prepared by sellers providing pricing for standard items that have been clearly defined by the buyer

## Slide 20: Figure 12-4. Request for Proposal (RFP) Template

## Slide 21: Evaluation Criteria
It’s important to prepare some form of evaluation criteria, preferably before issuing a formal RFP or RFQ
Beware of proposals that look good on paper; be sure to evaluate factors, such as past performance and management approach
Can require a technical presentation as part of a proposal

## Slide 22: Conducting Procurements
Deciding whom to ask to do the work
Sending appropriate documentation to potential sellers
Obtaining proposals or bids
Selecting a seller
Awarding a contract

## Slide 23: Figure 12-5. Sample Proposal Evaluation Sheet

## Slide 24: Seller Selection
Organizations often do an initial evaluation of all proposals and bids and then develop a short list of potential sellers for further evaluation
Sellers on the short list often prepare a best and final offer (BAFO)
Final output is a contract signed by the buyer and the selected seller

## Slide 25: Administering Procurements
Ensures that the seller’s performance meets contractual requirements
Contracts are legal relationships, so it is important that legal and contracting professionals be involved in writing and administering contracts
It is critical that project managers and team members watch for constructive change orders, which are oral or written acts or omissions by someone with actual or apparent authority that can be construed to have the same effect as a written change order

## Slide 26: Suggestions for Change Control in Contracts
Changes to any part of the project need to be reviewed, approved, and documented by the same people in the same way that the original part of the plan was approved
Evaluation of any change should include an impact analysis; how will the change affect the scope, time, cost, and quality of the goods or services being provided?
Changes must be documented in writing; project team members should also document all important meetings and telephone phone calls

## Slide 27: Suggestions for Change Control in Contracts (continued)
Project managers and teams should stay closely involved to make sure the new system will meet business needs and work in an operational environment
Have backup plans
Use tools and techniques, such as a contract change control system, buyer-conducted performance reviews, inspections and audits, and so on

## Slide 28: Best Practice
Accenture developed a list of best practices from experienced outsourcers throughout the world:
  Build in Broad Business Outcomes Early and Often
  Hire a Partner, Not Just a Provider
  It’s More Than a Contract, It’s a Business Relationship
  Leverage Gain-Sharing
  Use Active Governance
  Assign a Dedicated Executive
  Focus Relentlessly on Primary Objectives

## Slide 29: Closing Procurements
Involves completing and settling contracts and resolving any open items
The project team should:
  Determine if all work was completed correctly and satisfactorily
  Update records to reflect final results
  Archive information for future use
The contract itself should include requirements for formal acceptance and closure

## Slide 30: Tools to Assist in Contract Closure
Procurement audits identify lessons learned in the procurement process
Negotiated settlements help close contracts more smoothly
A records management system provides the ability to easily organize, find, and archive procurement-related documents

## Slide 31: Chapter Summary
Project procurement management involves acquiring goods and services for a project from outside the performing organization
Processes include:
  Plan procurements
  Conduct procurements
  Administer procurements
  Close procurements