## Slide 1: Chapter 4: Project Integration Management
Information Technology Project Management, Sixth Edition
Note: See the text itself for full citations.

## Slide 2: Announcements
8/25 – Chapter 1, Syllabus and Class Overview
9/1 – Chapter 2, Term Project Guidance, Team Breakouts
9/8 – Chapter 3, Team Breakouts
9/15 – Chapter 4, Team Breakouts
9/22 – Chapter 5, Team Breakouts
9/29 – No Class, Thursday follows Monday schedule….
10/6 – Chapter 6, Team Breakouts
10/13 – Midterm (chapters 1-6)
10/20 – 1st Team Presentations, due and presented.
Information Technology Project Management, Sixth Edition

## Slide 3: Learning Objectives
Describe an overall framework for project integration management as it relates to the other PM knowledge areas and the project life cycle
Explain the strategic planning process and apply different project selection methods
Project Financials….

## Slide 4: A Key to Overall Project Success: Project Integration Management
Project managers (the good ones) coordinate all knowledge areas throughout a project’s life cycle
Many new and seasoned project managers have trouble looking at the “big picture” and want to focus on
  There are too many details at times, time, scope, cost, resources etc… remember not to get too focused on one as your project can fail if you neglect the other KA’s
Note: Project integration management is not the same thing as software integration

## Slide 5: Project Management Framework – 9 Knowledge Areas

## Slide 6: Project Management Process Groups and Knowledge Area Mapping*

## Slide 7: Project Integration Management Processes (6 of them)
Develop the project charter
Develop the project management plan
Direct and manage project execution
Monitor and control the project work
Perform integrated change control
Close the project or phase

## Slide 8: Project Integration Management Processes
Develop the project charter: working with stakeholders to create the document that formally authorizes a project : the charter
Develop the project management plan: coordinating all planning efforts to create a consistent, coherent document
  Note: the project management plan is different from a Gantt Chart
Direct and manage project execution: carrying out the project management plan by performing the activities included in it

## Slide 9: Project Integration Management Processes (continued)
Monitor and control the project work: overseeing project work to meet the OVERALL performance objectives of the project
Perform integrated change control: coordinating changes that affect the project’s deliverables and organizational process assets
Close the project or phase: finalizing all project activities to formally close the project or phase

## Slide 10: Figure 4-1. Project Integration Management Summary

## Slide 11: Project Charters
After deciding what project to work on, it is important to let the rest of the organization know
A project charter is a document that formally recognizes the existence of a project and provides direction on the project’s objectives and management
Key project stakeholders should sign a project charter to acknowledge agreement on the need and intent of the project; a signed charter is a key output of project integration management

## Slide 12: Table 4-1. Project Charter for the DNA-Sequencing Instrument Completion Project

## Slide 13: Table 4-1. Charter (continued)

## Slide 14: Project Management Plans
A project management plan is a document used to coordinate all the project planning documents and help guide execution and control
    Think of it as the master plan, taking all 9-knowledge area plans into account and having a master document, cost plan, time plan, risk plans etc…
Plans created in the other knowledge areas are subsidiary parts of the overall project management plan

## Slide 15: Common Elements of a Project Management Plan
Introduction or overview of the project
Description of how the project is organized
Management and technical processes used on the project
Work to be done, schedule, and budget information

## Slide 16: Table 4-2. Sample Contents for a Software Project Management Plan (SPMP)

## Slide 17: Project Execution
Project execution involves managing and performing the work described in the project management plan
The majority of time and money is usually spent on execution

## Slide 18: Coordinating Planning and Execution
Project planning and execution are intertwined and inseparable activities
Key: Those who will do the work should help to plan the work
Key: Project managers must solicit input from the team to develop realistic plans

## Slide 19: Important Skills for Project Execution
General management skills like leadership, communication, and political skills
Product, organization, and business area skills and knowledge are needed
Use of specialized tools and techniques can be helpful to move work/execution along

## Slide 20: Project Execution Tools and Techniques
Expert judgment: experts can help project managers and their teams make many decisions related to project execution
Project management information systems:
  there are hundreds of project management software products available on the market today
  many organizations are moving toward powerful enterprise project management systems that are accessible via the Internet and mobile
    They aim to give centralized view of a project (all project artifacts in one place)
    And a portfolio view of all your programs/projects (in the same place etc…)

## Slide 21: Monitoring and Controlling Project Work
Changes are inevitable on most projects, so it’s important to develop and follow a process to monitor and control changes
Monitoring project work includes collecting, measuring, and disseminating performance information
A baseline is the initial approved project management plan

## Slide 22: Integrated Change Control
Three main objectives are:
  1) Identify and validate the change, and if the change is needed
    If so
  2) Manage the actual changes as they occur (plan, notify, execute, close it out)
  3)Determine if the change has occurred and report on if it made the impact or fix as intended

## Slide 23: Change Control on Information Technology Projects
Former view: the project team should strive to do exactly what was planned on time and within budget
  Problem: stakeholders rarely agreed up-front on the project scope, and time and cost estimates were inaccurate
Modern view: project management is a process of constant communication, negotiation and flexibility
  Solution: changes are often beneficial, and the project team should plan and control them and most of all communicate them early / often

## Slide 24: Table 4-3. Suggestions for Performing Integrated Change Control

## Slide 25: Change Control Board (CCB)
A formal group of people responsible for reviewing and approving or rejecting changes to a project
CCBs provide guidelines for preparing change requests, evaluate change requests, and manage the implementation of approved changes
Can include stakeholders from the entire organization
Also sometimes called a CAB – Change Advisory Board

## Slide 26: Closing Projects and Phases
To close a project or phase, you must finalize all activities and transfer the completed or cancelled work to the appropriate people
Main outputs include:
  Final product, service, or result transition
  Organizational process asset updates

## Slide 27: Strategic Planning and Project Selection
Strategic planning involves determining long-term objectives, predicting future trends, and projecting the need for new products and services
Organizations often perform a SWOT analysis
  Analyzing Strengths, Weaknesses, Opportunities, and Threats
As part of strategic planning, organizations:
  Identify potential projects
  Use realistic methods to select which projects to work on
  Formalize project initiation by issuing a project charter

## Slide 28: Figure 4-2. Mind Map of a SWOT Analysis to Help Identify Potential Projects

## Slide 29: Methods for Selecting Projects
There are usually more projects than available time and resources to implement them
Methods for selecting projects include:
  Focusing on broad organizational needs
  Categorizing information technology projects
  Performing net present value or other financial analyses
  Using a weighted scoring model
  Implementing a balanced scorecard

## Slide 30: Focusing on Broad Organizational Needs
It is often difficult to provide strong justification for many IT projects, but everyone agrees they have a high value
“It is better to measure gold roughly than to count pennies precisely”
Three important criteria for projects:
  There is a need for the project
  There are funds available
  There’s a strong will to make the project succeed

## Slide 31: Categorizing IT Projects
One categorization is whether the project addresses:
  A problem
  An opportunity, or
  A directive
Another categorization is how long it will take to do and when it is needed
Complex
And overall priority of the project

## Slide 32: Financial Analysis of Projects
Financial considerations are often an important consideration in selecting projects
Three primary methods for determining the projected financial value of projects:
  Net present value (NPV) analysis
  Return on investment (ROI)
  Payback analysis

## Slide 33: Net Present Value Analysis
Net present value (NPV) analysis is a method of calculating the expected net monetary gain or loss from a project by discounting all expected future cash inflows and outflows to the present point in time
  Simply put would I rather spend money today vs in the future, what's the time value of money worth to a company….
Projects with a positive NPV should be considered if financial value is a key criterion,
  The higher the NPV, the better

## Slide 34: Figure 4-4. Net Present Value Example

## Slide 35: Return on Investment
Return on investment (ROI) is calculated by subtracting the project costs from the benefits and then dividing by the costs
  ROI = (total discounted benefits - total discounted costs) / discounted costs
The higher the ROI, the better
Many organizations have a required rate of return or minimum acceptable rate of return on investment for projects

## Slide 36: Payback Analysis
Another important financial consideration is payback analysis
This is the payback period or the amount of time it will take to recoup invested money.
Payback occurs when the net cumulative discounted benefits equals the costs
Many organizations want IT projects to have a fairly short payback period, WHY?

## Slide 37: Figure 4-6. Charting the Payback Period

## Slide 38: Weighted Scoring Model
A weighted scoring model is a tool that provides a systematic process for selecting projects based on many criteria
    Identify criteria important to the project selection process
    Assign weights (percentages) to each criterion so they add up to 100%
    Assign scores to each criterion for each project
    Multiply the scores by the weights and get the total weighted scores
The higher the weighted score, the better

## Slide 39: Figure 4-7. Sample Weighted Scoring Model for Project Selection